## Sheet1
Issue | Description | Attachments | Status | Category | Assignee | Reporter | Reported On | Priority | Effort |  | Milestone | Linked To | Client Status | Status Changed On
[9 empty] | Development | Consumed
CPFA-I-6566 - login page ->forget password not working | login page ->forget password not working |  | Issue Raised | client + admin both |  | Aditi Chattopadhyay | 06-02-2025 |  |  |  | Milestone 6
Release Version No:
Platform: Desktop Web
Device: Chrome
Device Version: Chrome 14.1.1
CPFA-I-6564 - The assign/Inactive providers section load more button is not clickable whether showing 6 providers is present there but only 4 in visible. | The assign/Inactive providers section load more button is not clickable whether showing 6 providers is present there but only 4 in visible. | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e49aab04f78a3c3d1dbbe2402d98bfe1e3891787f33ff597ad3a6c17c5245dd06d6dafcb013147991e69aed46def12ebc3edf5e04890bde597c7dc63c4b748d2e, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 06-02-2025 |  |  |  | Milestone 6
Release Version No:
Platform: iOS / Android / Desktop Web / Mobile Web
Device: iPhone XR, iPhone 12 / Samsung Galaxy / Chrome, Safari / Chrome, Safari
Device Version: iOS 14 / Android 15 / Chrome 14.1.1
CPFA-I-6562 - Assign/Inactive Games section after assigned or inactive is done page should be refreshed. | Assign/Inactive Games section after assigned or inactive is done page should be refreshed. | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e1bd5dd93b87b6c36a9b085ecb0ffe77ae0f09765d2c1f6048b75ee79b1683cda3123a6b05e40f66747d6d177d77bd066bdc94b01b5c76bf0a77a0492cc747bc6, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 06-02-2025 | High |  |  | Milestone 6
Release Version No:
Platform: iOS / Android / Desktop Web / Mobile Web
Device: iPhone XR, iPhone 12 / Samsung Galaxy / Chrome, Safari / Chrome, Safari
Device Version: iOS 14 / Android 15 / Chrome 14.1.1
CPFA-I-6561 - Assign/Inactive Games is an aggregator super difficult to understand. | Assign/Inactive Games is an aggregator super difficult to understand. |  | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 06-02-2025 |  |  |  | Milestone 6
Release Version No:
Platform: Desktop Web
Device: Chrome
Device Version: Chrome 14.1.1
CPFA-I-6560 - not able to add region, after adding region it shows save/ added successfully but in the section it is not showing | not able to add region, after adding region it shows save/ added successfully but in the section it is not showing. |  | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 06-02-2025 |  |  |  | Milestone 6
Release Version No:
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6559 - Add Region section without entering any data in the user click add there is no any error pop up showing | Add Region section without entering any data in the user click add there is no any error pop up showing | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e1bd5dd93b87b6c36a9b085ecb0ffe77ae5586f7414ac07fe06bda3dd252b36962f92e13aa4decacb4bec40ecaa3ed897ef62bf6067e6799896da357ce551aff1, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 06-02-2025 |  |  |  | Milestone 6
Release Version No:
Platform: Desktop Web
Device: Chrome
Device Version: Chrome 14.1.1
CPFA-I-6558 - Add Currency section users enter any text or currency without saving if they click cancel and then click add currency the previous data is still showing there | Add Currency section users enter any text or currency without saving if they click cancel and then click add currency the previous data is still showing there | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e1bd5dd93b87b6c36a9b085ecb0ffe77a4e81d338e7f31adfe3be961fd7d2baf9d75fa04bfbde0889973228dda9f617a177395cd670daeee1df2041dba2e9d929, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 06-02-2025 |  |  |  | Milestone 6
​Release Version No:
Platform: Desktop Web
Device: Chrome
Device Version: Chrome 14.1.1​
CPFA-I-6557 - after entering the money value in admin click enter for a long time, the same money was added multiple times. | admin -> wallet management -> update wallet balance -> |  | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 06-02-2025 | High |  |  | Milestone 6
after entering the money value in admin click enter for a long time, the same money was added multiple times.
https://share.nmblc.cloud/3bcceb66
​Release Version No:
​Platform: Desktop Web
Device: Chrome
Device Version: Chrome 14.1.1​
CPFA-I-6556 - Remember me button is missing on the login page. | Remember me button is missing on the login page. |  | Issue Raised | client + admin both |  | Aditi Chattopadhyay | 06-02-2025 |  |  |  | Milestone 6
Release Version No:
Platform: Desktop Web
Device: Chrome
Device Version: Chrome 14.1.1
CPFA-I-6552 - Game list -> The game list section loads more sections not able to be used after the 25th but it shows the user there will be 30 games is present but after 25 it not showing. please check the screen short | The game list section loads more sections not able to be used after the 25th but it shows the user there will be 30 games is present but after 25 it not showing. please check the screen shot | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ea29814fd164c7d2973c74d28ad04a6b5ef7694f1a1ab45a9a71ce950eca68d6806ec92939efa318015c8977effe592f29b7ab5764d226bb3fb349ca43f4f2b87609d4872ea289544361a47dea44880cd712784cdbe6be2cbc79bc78a3270dbfc, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 05-02-2025 |  |  |  | Milestone 6
Release Version No:
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6549 - Assign/Inactive providers -> after Assign or inactive providers select then assigned them provider list should be saved and save as default , foe user understanding that whom they assigned or inactive in which fields | Assign/Inactive providers -> after Assign or inactive providers select then assigned them provider list should be saved and save as default , foe user understanding that whom they assigned or inactive in which fields ,,other wish admin assigned same field multiple times for one user | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e28c9950363f8e854e9c194164b0de08b51ce01b1e538519aabd398e4c2cced1e967b40e515a9df0f2c9d9c0f98c2dfe1810182c07d097a83b7fee0a6639d64f9, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 04-02-2025 |  |  |  | Milestone 6
Release Version No: -
Platform: Desktop Web
Device: Chrome
Device Version: Chrome 14.1.1
CPFA-I-6542 - Add Provider section in logo section if user paste any URL link then It will be saved but not showing any data , add validation in this part | Add Provider section in logo section if user paste any URL link then It will be saved but not showing any data , add validation in this part | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e85f84e232d4b89a9ccd2269c8f42bb2b1b0065478f2a90a0bb81a81ccb07f11bc13fd322c64b5206a14e958c28d23e2c2d0f571db6ca1fc842ee2b1246f9a055a0856f609b1dfe34dcaee56030352212586b472ab772da72f8096b3908f889c1, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 04-02-2025 |  |  |  | Milestone 6
Release Version No:
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6541 - caret icon is not working for navigation panel. | caret icon is not working for navigation panel. | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e204fcdf9228d2c9f30254f5d8cec74cd5bc17fe331c608d24fede5fd810220e1f151ba9262f4cc5457823d884d631c8ef55fab6cf3c91298d3dd7eeea09694e6, | Issue Raised | client + admin both |  | Aditi Chattopadhyay | 04-02-2025 |  |  |  | Milestone 6
​Release Version No:
​- Platform: Desktop Web
​- Device: Chrome
​- Device Version: Chrome 14.1.1​
CPFA-I-6540 - CurrencAdd Provider section showing user that Provider Name * and Currencies only mandatory field ,but after filed when user click ADD button it not working also no error message is showing that section ies | Add Provider section showing user that Provider Name * and Currencies only mandatory field ,but after filed when user click ADD button it not working also no error message is showing that section | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e204fcdf9228d2c9f30254f5d8cec74cde9510d03414dba3ad09e0989a62f1eb54ea77012203beaac0c9968df9b12a4b131632eb00e8c96a3a5aab55c6c39838f, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 04-02-2025 | High |  |  | Milestone 6
Release Version No:
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6539 - Add Provider section the gap between the field and the validation message should be minimized. | Add Provider section the gap between the field and the validation message should be minimized. | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e204fcdf9228d2c9f30254f5d8cec74cd6362e11ba480e43dfb4d1af15c28ff5b0c7293ae63b92ca811369559b88879ac8ced0cd730230d2db9d39a36b9f5ce54, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 04-02-2025 | Low |  |  | Milestone 6
Release Version No:
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6538 - client list -> Manage Account ->validation pop up message should be removed after 5 to 10 second and also if user open another slider then it must be removed . example -> error message came in Transactions page , then when user click Manage Provide | client list -> Manage Account ->validation pop up message should be removed after 5 to 10 second and also if user open another slider then it must be removed . | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e204fcdf9228d2c9f30254f5d8cec74cd7e377b7d87df033df7f52f7b06360658b50edb046fc86960fcafbf6be385ade99ede4ba7794626d50f4aa9a2d50c94b0, https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e204fcdf9228d2c9f30254f5d8cec74cd47c84e291b7a0fadd3f5c0a6c6b3616aedd674a57b5ccd245d3396d90169f0eb16cfd93f1ab7a0c48073eb39f080e511, https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e204fcdf9228d2c9f30254f5d8cec74cdfa2aa5759ea3b83c8b934c50c249b5b7a4c7144d32c953cce8561e89e95e9a0eb140021949957dfe0aba34604bdbbf21, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 04-02-2025 | Medium |  |  | Milestone 6
example -> error message came in Transactions page , then when user click Manage Providers, Manage Games that time previous message still present there
Release Version No:
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6537 - Manage AccountManage Account-> date filter not working properly if I click clear in the filter section then date section removed and a error message is showing after click search button that -> ValidationError: "start_date" with value "Invalid date | Manage Account-> date filter not working properly if I click clear in the filter section then date section removed and a error message is showing after click search button that -> | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e204fcdf9228d2c9f30254f5d8cec74cd70a21cb76c6033213ccd41126ffc21090cf8c48f2d37eb1ea4dd78ba634ee12857ef300bfee6bf549c7972d80d5bab21, | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 04-02-2025 |  |  |  | Milestone 6
ValidationError: "start_date" with value "Invalid date" fails to match the required pattern: /^\d{4}-\d{2}-\d{2} \d{2}:\d{2}:\d{2}$/
​Release Version No:
​- Platform: Desktop Web
​- Device: Chrome
​- Device Version: Chrome 14.1.1​
​
CPFA-I-6518 - pop up message timing in-between 5-10 second | pop up message timing in-between 5-10 second |  | Issue Raised | client + admin both |  | Aditi Chattopadhyay | 31-01-2025 |  |  |  | Milestone 6
CPFA-I-6516 - game management ->upload new games section instruction need to be shown | game management ->upload new games section instruction need to be shown |  | Issue Raised | - |  | Aditi Chattopadhyay | 31-01-2025 |  |  |  | Milestone 6
CPFA-I-6512 - when user try to login resend otp button active for 1 sec ad then got deactivated | when user try to login resend otp button active for 1 sec ad then got deactivated |  | Issue Raised | client + admin both |  | Aditi Chattopadhyay | 31-01-2025 |  |  |  | Milestone 6
​Release Version No:
​- Platform: Desktop Web
​- Device: Chrome
​- Device Version: Chrome 14.1.1​
CPFA-I-6511 - Game Category section search button not working . | Game Category section search button not working . | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e31b3c5155c8162ab769265722a03411ad0f8e3c1affb119cc04f75be02bde9fea1d1479816935c297c1cd29b3328e1948cd5f1f9b81ac20b1b2a81d22fd2bcd2, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6510 - Game Category section after adding new Category it not showing , after page refreshed it able to show | Game Category section after adding new Category it not showing , after page refreshed it able to show |  | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6509 - the gap between the field and the validation message should be minimized | the gap between the field and the validation message should be minimized | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e31b3c5155c8162ab769265722a03411a6b6ca14d66512f6812b5f4e490f2fc1e258bd426ca09e41edd3d00c53384a8aa40bd7f95f7f21bb4354bde78c25dc423, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6508 - Client List section after user filter if user click action button then a scroll appear and also Update Client Change Password Account List not able to show properly , after scroll it able to show, fixed this to show total list properly after click ac | Client List section after user filter if user click action button then a scroll appear and also Update Client Change Password Account List not able to show properly , after scroll it able to show, fixed this to show total list properly after click action button | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e31b3c5155c8162ab769265722a03411a5b3095cf4dd7943c212bac7e5eeb86563a3064e66199c520fa36d0d5987445f20ff6ce81d0369b91a057fad117674ed4, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6505 - add wallet balance ->stop able to add 0in wallet, if user add 0 in wallet it processed successfully | add wallet balance ->stop able to add 0in wallet, if user add 0 in wallet it processed successfully |  | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6504 - add wallet balance -> not able to add money if I write e2 , but in money section only numbers should be write here user able to write "e", | add wallet balance -> not able to add money if I write e2 , but in money section only numbers should be write here user able to write "e", | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e31b3c5155c8162ab769265722a03411a11be3dd9ba745f20d8c37d5b1542c16e462982613e640482a4c9a573fd116e47c42f86ddab71b84719cefc15d88a608f, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6502 - Transaction Wallet History pop up not closed .from this page if I try to change credit balance as JPY or others which is already empty means no transaction wallet history present that time pop up not getting closed |  | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e31b3c5155c8162ab769265722a03411a571af73ea3d8e3848f412d06b4c3688a94c74cac3f96bfb7233605323348a6b03c3812f8fa6365c8c69ae9ceb7659147, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Transaction Wallet History pop up not closed .from this page if I try to change credit balance as JPY or others which is already empty means no transaction wallet history present that time pop up not getting closed
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6501 - client -> last 3 months date showing wrong data. please check this | client -> last 3 months date showing wrong data. please check this | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ecd83cddec41ff8a022feb637e85943fafce789255561ef0484f9d3e71263b1c685ba712c215a414b90d9139e9d3ab52df40f453fa8d23c2519e2ef155c14a93d, https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ecd83cddec41ff8a022feb637e85943face4d4e1b4b4f9bc6e473285201e3fdaef8559927c772c80155739c79e36f199e63fddc9d654622f02cac78caaf972e07, | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Desktop Web
- Device: Chrome- Chrome 14.1.1
CPFA-I-6499 - player list -> search player list not working . when I try to search any name which is present it showing not found | player list -> search player list not working . when I try to search any name which is present it showing not found | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ecd83cddec41ff8a022feb637e85943fa17b96bb91e5dcc2926fac018b24f9550b55fe9bc76e3113e2d64b83af879aea61830effb5632d2d4aaa0e173c52c4729, https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ecd83cddec41ff8a022feb637e85943fa8854f6a2ca836108462373bc2849f6a6fc82e016bab86eaa8165bdc79535a85c1112ef41779f536b4b730e3dabff0ae9, | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6498 - user details section Bet Count and total bet, Average RTP is missing | user details section Bet Count and total bet, Average RTP is missing. | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ecd83cddec41ff8a022feb637e85943face0d3f8b3197e037662d9e57b787ca0def41d46c8ce846ddfc59ea1f0467f829594dd3aec09530671a66db52ffa7cb83, | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 30-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6490 - client -> if user click profile button then not found page is showing | client -> if user click profile button then not found page is showing | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e13c909b14f317b1dbb7df36419344bae668298817eea29fb4c688a9e7cc1c92dcf39f604301cae6d851d0d289f9670255f89936046b676a4f453f9d6e881c73e, | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 29-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6480 - Assign/Inactive providers section search button not working. | Assign/Inactive providers section search button not working | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e13c909b14f317b1dbb7df36419344baeb195a2acebda6ed6ebe86ad56284097071fed52027a3622111351299e0a463b07cdfcbf590d5c0e1639575c6fa67e0d2, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 29-01-2025 |  |  |  | Milestone 6
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6479 - Assign/Inactive providers -> previous time assigned things need to shown in a another list , called assigned account /assigned providers if admin assigned some ting already it must be shown in the list , same things no able to assign again . | Assign/Inactive providers -> previous time assigned things need to shown in a another list , called assigned account /assigned providers | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e46bcd44d4a842c1f3cc9017ddd8e14b99c8c6da9b7b3fab3de0367da12583233a47e0b19edae80e3afb0f5d98e3866e53b23178beba3c50963276ea4862d18ee, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 29-01-2025 |  |  |  | Milestone 6
if admin assigned some ting already it must be shown in the list , same things no able to assign again .
Release Version No: v 1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6477 - The amount will be credited to the client account but on the top right corner the balance is getting change on KRW account it should change on Euro account. ,Also in debit section same tings happened. | The amount will be credited to the client account but on the top right corner the balance is getting change on KRW account it should change on Euro account. ,Also in debit section same tings happened. |  | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 29-01-2025 | High |  |  | Milestone 6
seems like backend is ok issue is in frontend section
open client list
choose Aditi client and open it
open account list
make sure KRW should selected from to the right corner
now choose ok account and click on "Transfer Balance "
then try to credit amount
put value 10 on credit amount and click credit button.
pop up come lick yes
then check balance ​was change .
CPFA-I-6459 - resent otp button not working when user click resent an error message is showing that "The entered username does not exist. " | resent otp button not working when user click resent an error message is showing that "The entered username does not exist. "​ | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ecceec22d1f828e4da1239f6053eb3ce4e9f33d3bf77d9866cf9bd5f76fece9a5776c4fbaa004850cad1cabb9126be6a4cff39cbab2278be871c4bc856e341d66, | Issue Raised | client + admin both |  | Aditi Chattopadhyay | 28-01-2025 |  |  |  | Milestone 6
CPFA-I-6440 - super -> when I try to add balance in client panel money showing 80,112. ,Transfer Balance of aditi chatterjee for ok account but money not able to transfer | super -> when I try to add balance in client panel money showing 80,112. ,Transfer Balance of aditi chatterjee for ok account but money not able to transfer | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ecceec22d1f828e4da1239f6053eb3ce43fde3da284a9e7e146941c2dcd2ffa3b506380042483dd2037ad33dee1e709cb4a665d002040db3223d81354411f3c49, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 28-01-2025 |  |  |  | Milestone 6
Release Version No: v.1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6432 - aggregator super admin -> money is not debited form the admin wallet but process showing that its done and also in the debit credit page main balance update changed but actually it's not happen | aggregator super admin -> money is not debited form the admin wallet |  | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 28-01-2025 |  |  |  | Milestone 6
but process showing that its done and also in the debit credit page main balance update changed but actually it's not happen
CPFA-I-6429 - Assign/Inactive providers part error showing 8 times at one time. | Assign/Inactive providers part error showing 8 times at one time. | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e1b871bdfae381de13c86b7a227fb4bbd058021c3ff85b95cde2e751b29823bcffeb2196a053ff566e29777764b697d0b229e429df116a322b2cff264ba7a9930, | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 28-01-2025 | High |  |  | Milestone 6
CPFA-I-6427 - create a new ID and then add client id, after that when try to Assign/Inactive providers to assign provider to client then error occer that provider_id.map is not a function. | create a new ID and then add client id, after that when try to Assign/Inactive providers to assign provider to client then error occer that provider_id.map is not a function.​ |  | Issue Raised | Aggregator Super |  | Aditi Chattopadhyay | 28-01-2025 | High |  |  | Milestone 6
CPFA-I-6426 - when user click resent OTP 2nd time there is an error message came that "The entered username does not exist." and also in OTP page username message no need to shown | when user click resent OTP 2nd time there is an error message came that "The entered username does not exist." and also in OTP page username message no need to shown |  | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 28-01-2025 | High |  |  | Milestone 6
​Release Version No: v1.0
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6416 - login page -> The entered username does not exist." message not removed after a sometimes | login page -> The entered username does not exist." message not removed after a sometimes | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9ecf10d6f9352d4715c6a0c64a65266d771decd55566177afbae65340e683bdd3896b0ef9de6a2c8e5000fda281ca248784b2089faa4370214ae8ba59e3229db04, | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 27-01-2025 |  |  |  | Milestone 6
Release Version No:
Platform: Desktop Web
Device: Chrome
Device Version:Chrome 14.1.1
CPFA-I-6415 - login page ->Password is required. not set proper position .fixed time , | login page ->Password is required. not set proper position .fixed time , | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e24b586d12743d992293314b8b382e571121e3ad1467302779523108cc1b7f67342bdb82da0d848b96da94110950c1c613779c7a3bfbba4f10fdd218f6523e43f, | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 27-01-2025 |  |  |  | Milestone 6
- Release Version No:
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1
CPFA-I-6414 - login page -. > User Name is required. message shown under the username section . right now it's not , fixed this | login page -. > User Name is required. message shown under the username section . right now it's not , fixed this | https://api.redappletech.com/hrms/config/download?filename=b8368f32885ee64bbcd699dcb7923a9e24b586d12743d992293314b8b382e57118b2c0f68206763a4d9da557a3af38e96fcc71ac16d2b5ee3b46e8688616dae1273fa4d04f5a17c7d09425a904397161, | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 27-01-2025 |  |  |  | Milestone 6
Release Version No:
Platform: Desktop Web
Device: Chrome
Device Version: Chrome 14.1.1
CPFA-I-6409 - aggregator client -> dashboard not working . | aggregator client -> dashboard not working . |  | Issue Raised | aggregator client |  | Aditi Chattopadhyay | 27-01-2025 |  |  |  | Milestone 6
after login the dashboard is not working .just static data is showing
Release Version No: not mention
- Platform: Desktop Web
- Device: Chrome
- Device Version: Chrome 14.1.1