## Milestone Plan_V3
|  |  |  | Version :01 | Version: | Version: V.3
Game Name: | Jeeto joker |  |  |  | Date: | Date: 29th Jan 2024
Reference Game: | Jeeto joker (Video)
Service Required: | Design and Development
Game Engine: | Unity
Application Name: | ShipGudds Web & Mobile App
Service Required: | Design and Development
Technology Stack | Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb
MILESTONES | DELIVERABLES | Section | Module | Weeks | Start Date | End Date | Status
1 | UI/UX Design | Web application | Shipper and transporter | 4 Weeks | 2023-10-30 | 2023-11-24 | Paid
|  | Mobile application | Shipper and transporter
2 | Web, android and iOS application | Registration Module | Transporter Module | 3Weeks | 2024-01-29 | 2024-02-16 | Work in Progress
Login Module
Forgot Password Module
Subscription module for Transporter (without payment integration)
| Web, android and iOS application | Registration Module | Shipper Module
Login Module
Forgot Password Module
Subscription module for shipper (without payment integration)
| Admin Panel | Login and forgot password | Admin Module
List and manage Transporter details
Testing and Bug fixing
3 | Web, android and iOS application | Add Bank Details Module | Shipper Module | 3Weeks | 19/02/2024 | 08/03/2024
Shipper request posting
List of Recommended Transporters
Pending Request lists
| Web, android and iOS application | Onboarding Module | Transporter Module
Transporter settings (add vehicle, add godown, add payment , add cities, add user )update
Request list for Transporter
Bid, accept/reject requests
| Admin Panel | List and manage shippers details | Admin Module
Transporters Approvals
Testing and Bug fixing
4 | Web, android and iOS application | Bid/quote request accept/reject | Shipper Module | 4Weeks | 2024-03-11 | 2024-04-05
Review & accept/reject updated quote (in case quote modified by transporeter )
Update receiver name and contact details
eway bill upload/delivery document
| Web, android and iOS application | Bid/quote request accept/reject | Transporter Module
Updated quote if required
Driver / manager role based login
Assign driver module
| Admin Panel | Shipment Requests (view only) | Admin Module
Testing and Bug fixing
5 | Web, android and iOS application | Upload invoice | Transporter Module | 3Weeks | 2024-04-08 | 2024-04-26
Delivery start and end (otp on whatsapp)
| Web, android and iOS application | Payment and upload payment details | Shipper Module
Revceiver complete the shipment
Receiver history
Receiver pay if required
| Admin Panel | Payment Transactions History | Admin Module
Testing and Bug fixing
-
6 | Web, android and iOS application | Driver tracking and real time update (we have dependency on the device) | Shipper , transporter and receiver | 5Weeks | 2024-04-29 | 2024-05-31
Testing and Bug fixing
Note
1. We have a few dependencies like payment gateway, 3rd party API's for OCR and Verification process, google paid account for map integration
2. Will integrate payment gateway in the 3 rd milestone

## Resource Allocation_V3
|  | Version :01 | Version: V.1 |  |  |  |  | Version: | Version: V.3
Game Name: | Jeeto joker |  | Date: 8thJune2023 |  |  |  |  | Date: | Date: 29th Jan 2024
Reference Game: | Jeeto joker (Video)
Service Required: | Design and Development
Game Engine: | Unity
Application Name: | ShipGudds Web & Mobile App
Service Required: | Design and Development
Technology Stack | Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb
Resource | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15 | Week16 | Week17 | Week18 | Week19 | Week20
Designer | bar: Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week1 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week5
Android | bar: Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week4 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week20
iOS | bar: Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week4 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week20
Web app | bar: Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week2 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week7; Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week10 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week13; Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week15 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week20
Backend | bar: Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week2 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week15
Admin Panel | bar: Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week1; Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week8 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week9; Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week14
Tester | bar: Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week1 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week2; Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week8; Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week12; Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week15; Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week18 to Website: Reactjs, Admin Panel: Reactjs, IOS Application: Swift ,Android Application: Kotlin, API: Nodejs, Database: MySQL / Mongodb Week20
Project management